## tasks
id | code | name | type | status | oldStart | oldFinish | oldRemainingDurationHours | minDuration | maxDuration
106071 | 10 | EXCAVATION | TT_Task | TK_NotStart | 2013-09-16 12:00 | 2013-09-30 16:00 | 100
106222 | 20 | REPLACMENT LAYER | TT_Task | TK_NotStart | 2013-10-01 08:00 | 2013-10-10 14:00 | 70
106223 | 30 | BACKFILL | TT_Task | TK_NotStart | 2013-11-26 14:00 | 2013-12-04 16:00 | 50
106224 | 40 | P.C | TT_Task | TK_NotStart | 2013-10-10 14:00 | 2013-10-21 12:00 | 70
106225 | 50 | R.C | TT_Task | TK_NotStart | 2013-10-21 12:00 | 2013-11-07 12:00 | 120
106226 | 60 | NECK COLUMN | TT_Task | TK_NotStart | 2013-11-07 12:00 | 2013-11-18 10:00 | 70
106227 | 70 | SLAB ON GRADE | TT_Task | TK_NotStart | 2013-12-05 08:00 | 2013-12-08 12:00 | 20
106228 | 80 | DAMP PROOFING | TT_Task | TK_NotStart | 2013-11-23 08:00 | 2013-11-25 12:00 | 20
106229 | 90 | INSULATION | TT_Task | TK_NotStart | 2013-11-25 12:00 | 2013-11-26 14:00 | 10
106230 | 100 | BRICK WORK | TT_Task | TK_NotStart | 2013-11-18 10:00 | 2013-11-21 16:00 | 30
106231 | 110 | BASEMENT COLUMN | TT_Task | TK_NotStart | 2013-12-08 12:00 | 2013-12-18 10:00 | 70
106232 | 120 | BASEMENT SLAB | TT_Task | TK_NotStart | 2013-12-18 10:00 | 2014-01-02 14:00 | 100
106233 | 130 | GROUND COLUMN | TT_Task | TK_NotStart | 2014-01-02 14:00 | 2014-01-13 12:00 | 70
106234 | 140 | GROUND SLAB | TT_Task | TK_NotStart | 2014-01-13 12:00 | 2014-01-29 10:00 | 110
106235 | 150 | 1ST FLOOR COLUMN | TT_Task | TK_NotStart | 2014-01-29 10:00 | 2014-02-08 16:00 | 70
106236 | 160 | 1ST FLOOR SLAB | TT_Task | TK_NotStart | 2014-02-09 08:00 | 2014-02-23 12:00 | 100
106237 | 170 | 2ND FLOOR COLUMN | TT_Task | TK_NotStart | 2014-02-23 12:00 | 2014-03-05 10:00 | 70
106238 | 180 | 2ND FLOOR SLAB | TT_Task | TK_NotStart | 2014-03-05 10:00 | 2014-03-19 14:00 | 100
106239 | 190 | 3RD FLOOR COLUMN | TT_Task | TK_NotStart | 2014-03-19 14:00 | 2014-03-30 12:00 | 70
106240 | 200 | 3RD FLOOR SLAB | TT_Task | TK_NotStart | 2014-03-30 12:00 | 2014-04-13 16:00 | 100
106241 | 210 | ROOF FLOOR COLUMN | TT_Task | TK_NotStart | 2014-04-14 08:00 | 2014-04-21 10:00 | 50
106242 | 220 | ROOF FLOOR SLAB | TT_Task | TK_NotStart | 2014-04-21 10:00 | 2014-04-28 12:00 | 50
106243 | 230 | B. FLOOR MASONARY WORK | TT_Task | TK_NotStart | 2014-01-29 10:00 | 2014-02-02 16:00 | 30
106244 | 240 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-02-03 08:00 | 2014-02-23 12:00 | 140
106245 | 250 | PLASTER | TT_Task | TK_NotStart | 2014-02-12 14:00 | 2014-03-05 10:00 | 140
106246 | 260 | CERMIC | TT_Task | TK_NotStart | 2014-02-12 14:00 | 2014-02-19 16:00 | 50
106247 | 270 | INTIAL PAINTING | TT_Task | TK_NotStart | 2014-04-16 12:00 | 2014-05-04 12:00 | 120
106248 | 280 | GR. FLOOR MASONARY WORK | TT_Task | TK_NotStart | 2014-02-03 08:00 | 2014-02-16 10:00 | 90
106249 | 290 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-02-23 12:00 | 2014-03-15 16:00 | 140
106250 | 300 | PLASTER | TT_Task | TK_NotStart | 2014-03-05 10:00 | 2014-04-03 10:00 | 200
106251 | 310 | MATEL LATH | TT_Task | TK_NotStart | 2014-04-10 12:00 | 2014-04-16 12:00 | 40
106252 | 320 | CERMIC | TT_Task | TK_NotStart | 2014-02-20 08:00 | 2014-03-06 12:00 | 100
106253 | 330 | INTIAL PAINTING | TT_Task | TK_NotStart | 2014-05-22 14:00 | 2014-06-21 14:00 | 200
106254 | 340 | 1ST FLOOR MASONARY WORK | TT_Task | TK_Active | 2014-02-23 12:00 | 2014-03-11 10:00 | 110
106255 | 350 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-03-16 08:00 | 2014-04-05 12:00 | 140
106256 | 360 | PLASTER | TT_Task | TK_NotStart | 2014-04-03 10:00 | 2014-05-10 12:00 | 250
106257 | 370 | MATEL LATH | TT_Task | TK_NotStart | 2014-05-17 14:00 | 2014-05-22 14:00 | 40
106258 | 380 | CERMIC | TT_Task | TK_NotStart | 2014-03-22 08:00 | 2014-04-05 12:00 | 100
106259 | 390 | INTIAL PAINTING | TT_Task | TK_NotStart | 2014-06-30 10:00 | 2014-07-21 16:00 | 150
106260 | 400 | 2ND FLOOR MASONARY WORK | TT_Task | TK_NotStart | 2014-03-19 14:00 | 2014-04-03 10:00 | 100
106261 | 410 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-04-05 12:00 | 2014-04-24 16:00 | 140
106262 | 420 | PLASTER | TT_Task | TK_NotStart | 2014-05-10 12:00 | 2014-06-16 16:00 | 260
106263 | 430 | MATEL LATH | TT_Task | TK_NotStart | 2014-06-24 10:00 | 2014-06-30 10:00 | 40
106264 | 440 | CERMIC | TT_Task | TK_NotStart | 2014-04-14 08:00 | 2014-04-28 12:00 | 100
106265 | 450 | INTIAL PAINTING | TT_Task | TK_NotStart | 2014-08-03 08:00 | 2014-08-25 16:00 | 160
106266 | 460 | 3RD FLOOR MASONARY WORK | TT_Task | TK_NotStart | 2014-04-14 08:00 | 2014-04-28 12:00 | 100
106267 | 470 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-04-28 12:00 | 2014-05-18 16:00 | 140
106268 | 480 | PLASTER | TT_Task | TK_NotStart | 2014-06-17 08:00 | 2014-07-20 14:00 | 230
106269 | 490 | MATEL LATH | TT_Task | TK_NotStart | 2014-07-28 08:00 | 2014-08-02 16:00 | 40
106270 | 500 | CERMIC | TT_Task | TK_NotStart | 2014-05-08 10:00 | 2014-05-24 16:00 | 110
106271 | 510 | INTIAL PAINTING | TT_Task | TK_NotStart | 2014-08-26 08:00 | 2014-09-08 10:00 | 90
106272 | 520 | ROOF FLOOR MASONARY WORK | TT_Task | TK_NotStart | 2014-04-28 12:00 | 2014-04-30 16:00 | 20
106273 | 530 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-05-19 08:00 | 2014-05-28 14:00 | 70
106274 | 540 | PLASTER | TT_Task | TK_NotStart | 2014-07-20 14:00 | 2014-07-31 14:00 | 80
106275 | 550 | MATEL LATH | TT_Task | TK_NotStart | 2014-08-09 08:00 | 2014-08-13 16:00 | 40
106276 | 560 | PROOFING | TT_Task | TK_NotStart | 2014-07-31 14:00 | 2014-08-06 14:00 | 40
106277 | 570 | THERMAL INSULATION | TT_Task | TK_NotStart | 2014-08-06 14:00 | 2014-08-12 14:00 | 40
106278 | 580 | P. C. SCREED | TT_Task | TK_NotStart | 2014-08-12 14:00 | 2014-08-13 16:00 | 10
106279 | 590 | PLASTER | TT_Task | TK_NotStart | 2014-07-31 14:00 | 2014-08-25 16:00 | 170
106280 | 600 | CERETAL WORK | TT_Task | TK_NotStart | 2014-08-26 08:00 | 2014-09-15 12:00 | 140
106281 | 610 | PLASTER | TT_Task | TK_NotStart | 2014-08-26 08:00 | 2014-11-13 14:00 | 550
106282 | 620 | RED TILES | TT_Task | TK_NotStart | 2014-11-13 14:00 | 2014-11-20 16:00 | 50
106283 | 630 | WINDOWS&DOORS | TT_Task | TK_NotStart | 2014-05-04 12:00 | 2014-05-24 16:00 | 140
106284 | 640 | PAINTING | TT_Task | TK_NotStart | 2014-05-25 08:00 | 2014-06-08 12:00 | 100
106285 | 650 | WOODEN FLOORS | TT_Task | TK_NotStart | 2014-06-03 14:00 | 2014-06-14 12:00 | 70
106286 | 660 | MARBLE FLOORS | TT_Task | TK_NotStart | 2014-06-03 14:00 | 2014-06-18 10:00 | 100
106287 | 670 | FINISHING FLOORS | TT_Task | TK_NotStart | 2014-06-03 14:00 | 2014-06-14 12:00 | 70
106288 | 680 | ALUMINUM | TT_Task | TK_NotStart | 2014-05-04 12:00 | 2014-06-03 14:00 | 210
106289 | 690 | DOOR | TT_Task | TK_NotStart | 2014-06-14 12:00 | 2014-07-14 14:00 | 210
106290 | 700 | PAINTING | TT_Task | TK_NotStart | 2014-07-14 14:00 | 2014-07-30 12:00 | 110
106291 | 710 | WOODEN FLOORS | TT_Task | TK_NotStart | 2014-07-22 08:00 | 2014-08-11 12:00 | 140
106292 | 720 | MARBLE FLOORS | TT_Task | TK_NotStart | 2014-07-22 08:00 | 2014-07-31 14:00 | 70
106293 | 730 | FINISHING FLOORS | TT_Task | TK_NotStart | 2014-07-22 08:00 | 2014-07-31 14:00 | 70
106294 | 740 | ALUMINUM | TT_Task | TK_NotStart | 2014-06-21 14:00 | 2014-07-21 16:00 | 210
106295 | 750 | DOOR | TT_Task | TK_NotStart | 2014-07-31 14:00 | 2014-08-31 16:00 | 210
106296 | 760 | PAINTING | TT_Task | TK_NotStart | 2014-09-01 08:00 | 2014-09-15 12:00 | 100
106297 | 770 | WOODEN FLOORS | TT_Task | TK_NotStart | 2014-08-21 10:00 | 2014-09-10 14:00 | 140
106298 | 780 | MARBLE FLOORS | TT_Task | TK_NotStart | 2014-08-21 10:00 | 2014-08-28 12:00 | 50
106299 | 790 | FINISHING FLOORS | TT_Task | TK_NotStart | 2014-08-21 10:00 | 2014-08-31 16:00 | 70
106300 | 800 | ALUMINUM | TT_Task | TK_NotStart | 2014-07-22 08:00 | 2014-08-21 10:00 | 210
106301 | 810 | DOOR | TT_Task | TK_NotStart | 2014-09-01 08:00 | 2014-10-01 10:00 | 210
106302 | 820 | PAINTING | TT_Task | TK_NotStart | 2014-10-01 10:00 | 2014-10-16 16:00 | 110
106303 | 830 | WOODEN FLOORS | TT_Task | TK_NotStart | 2014-10-08 12:00 | 2014-10-28 16:00 | 140
106304 | 840 | MARBLE FLOORS | TT_Task | TK_NotStart | 2014-10-08 12:00 | 2014-10-15 14:00 | 50
106305 | 850 | FINISHING FLOORS | TT_Task | TK_NotStart | 2014-10-08 12:00 | 2014-10-19 10:00 | 70
106306 | 860 | ALUMINUM | TT_Task | TK_NotStart | 2014-09-08 10:00 | 2014-10-08 12:00 | 210
106307 | 870 | DOOR | TT_Task | TK_NotStart | 2014-10-19 10:00 | 2014-11-18 12:00 | 210
106308 | 880 | PAINTING | TT_Task | TK_NotStart | 2014-11-18 12:00 | 2014-12-01 14:00 | 90
106309 | 890 | CEMENT TILES | TT_Task | TK_NotStart | 2014-08-14 08:00 | 2014-08-27 10:00 | 90
106310 | 900 | FACADES PLASTER | TT_Task | TK_NotStart | 2014-08-27 10:00 | 2014-09-09 12:00 | 90
106311 | 910 | DOOR | TT_Task | TK_NotStart | 2014-11-18 12:00 | 2014-11-29 10:00 | 70
106312 | 920 | CERETAL WORK | TT_Task | TK_NotStart | 2014-07-26 14:00 | 2014-08-25 16:00 | 210
106313 | 930 | PLASTER COLORD | TT_Task | TK_NotStart | 2014-09-02 10:00 | 2014-09-21 12:00 | 130
106314 | 940 | MARBLE FLOORS | TT_Task | TK_NotStart | 2014-09-21 12:00 | 2014-10-02 12:00 | 80
106315 | 950 | MARBLE STAIRS | TT_Task | TK_NotStart | 2014-09-21 12:00 | 2014-10-04 14:00 | 90
106316 | 960 | FACADES PLASTER DAHARA | TT_Task | TK_NotStart | 2014-11-22 08:00 | 2015-01-18 16:00 | 400
106317 | 970 | BARGOLAS | TT_Task | TK_NotStart | 2015-01-19 08:00 | 2015-01-26 10:00 | 50
106318 | 980 | INTIAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-02-03 08:00 | 2014-02-12 14:00 | 70
106319 | 990 | FINAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-02-20 08:00 | 2014-02-24 14:00 | 30
106320 | 1000 | INTIAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-02-16 10:00 | 2014-02-25 16:00 | 70
106321 | 1010 | FINAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-03-06 12:00 | 2014-03-11 10:00 | 30
106322 | 1020 | INTIAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-03-11 10:00 | 2014-03-20 16:00 | 70
106323 | 1030 | FINAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-04-05 12:00 | 2014-04-09 10:00 | 30
106324 | 1040 | INTIAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-04-03 10:00 | 2014-04-13 16:00 | 70
106325 | 1050 | FINAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-04-28 12:00 | 2014-05-03 10:00 | 30
106326 | 1060 | INTIAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-04-28 12:00 | 2014-05-08 10:00 | 70
106327 | 1070 | FINAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-05-25 08:00 | 2014-05-28 14:00 | 30
106328 | 1080 | INTIAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-05-08 10:00 | 2014-05-12 16:00 | 30
106329 | 1090 | FINAL SAINTARY WORK | TT_Task | TK_NotStart | 2014-05-28 14:00 | 2014-06-01 10:00 | 20
106330 | 1100 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-02-23 12:00 | 2014-03-09 16:00 | 100
106331 | 1110 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-03-05 10:00 | 2014-03-12 12:00 | 50
106332 | 1120 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-06-08 12:00 | 2014-06-18 10:00 | 70
106333 | 1130 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-03-16 08:00 | 2014-03-30 12:00 | 100
106334 | 1140 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-04-03 10:00 | 2014-04-10 12:00 | 50
106335 | 1160 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-07-30 12:00 | 2014-08-13 16:00 | 100
106336 | 1170 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-04-05 12:00 | 2014-04-19 16:00 | 100
106337 | 1180 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-05-10 12:00 | 2014-05-17 14:00 | 50
106338 | 1190 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-09-15 12:00 | 2014-09-29 16:00 | 100
106339 | 1200 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-04-26 08:00 | 2014-05-10 12:00 | 100
106340 | 1210 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-06-17 08:00 | 2014-06-24 10:00 | 50
106341 | 1220 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-10-18 08:00 | 2014-11-01 12:00 | 100
106342 | 1230 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-05-19 08:00 | 2014-06-02 12:00 | 100
106343 | 1240 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-07-20 14:00 | 2014-07-27 16:00 | 50
106344 | 1250 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-12-01 14:00 | 2014-12-16 10:00 | 100
106345 | 1260 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-06-02 12:00 | 2014-06-16 16:00 | 100
106346 | 1270 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-07-31 14:00 | 2014-08-07 16:00 | 50
106347 | 1280 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-12-16 10:00 | 2014-12-25 16:00 | 70
106348 | 1290 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-06-17 08:00 | 2014-07-01 12:00 | 100
106349 | 1300 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-08-26 08:00 | 2014-09-02 10:00 | 50
106350 | 1310 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2015-01-26 10:00 | 2015-02-09 14:00 | 100
106351 | 1320 | 1ST ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-07-01 12:00 | 2014-07-12 10:00 | 70
106352 | 1330 | 2ND ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-11-13 14:00 | 2014-11-20 16:00 | 50
106353 | 1340 | FINAL ELECTRICAL FIX | TT_Task | TK_NotStart | 2014-11-22 08:00 | 2014-11-26 16:00 | 40
106354 | 1350 | ELEVATOR | TT_Task | TK_NotStart | 2015-02-09 14:00 | 2015-02-19 12:00 | 70
106355 | 1360 | final fisihes closeout | TT_Task | TK_NotStart | 2015-01-26 10:00 | 2015-01-26 10:00 | 0
106356 | 1370 | mechincal closeout | TT_Task | TK_NotStart | 2014-06-01 10:00 | 2014-06-01 10:00 | 0
106357 | 1380 | electrical closeout | TT_Task | TK_NotStart | 2015-02-09 14:00 | 2015-02-09 14:00 | 0
106358 | 1390 | confeying closeout | TT_Task | TK_NotStart | 2015-02-19 12:00 | 2015-02-19 12:00 | 0
106559 | 1400 | PROJECT START | TT_Mile | TK_NotStart | 2013-08-03 08:00 | 2013-08-03 08:00 | 0
106560 | 1410 | R.C SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-08-03 08:00 | 2013-08-10 10:00 | 50
106561 | 1420 | R.C SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-08-10 10:00 | 2013-08-17 12:00 | 50
106564 | 1450 | B.COL. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-08-10 10:00 | 2013-08-17 12:00 | 50
106565 | 1460 | B.COL SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-08-17 12:00 | 2013-08-24 14:00 | 50
106566 | 1470 | GR.COL. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-08-24 14:00 | 2013-08-31 16:00 | 50
106567 | 1480 | GR.COL SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-09-01 08:00 | 2013-09-09 10:00 | 50
106568 | 1490 | 1ST COL. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-09-09 10:00 | 2013-09-16 12:00 | 50
106569 | 1500 | 1ST COL SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-09-16 12:00 | 2013-09-23 14:00 | 50
106570 | 1510 | 2ND COL. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-09-23 14:00 | 2013-09-30 16:00 | 50
106571 | 1520 | 2ND COL SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-10-01 08:00 | 2013-10-08 10:00 | 50
106572 | 1530 | 3RD COL. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-10-15 12:00 | 2013-10-22 14:00 | 50
106573 | 1540 | 3RD CO. SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-10-22 14:00 | 2013-10-29 16:00 | 50
106574 | 1550 | ROOF COL. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-10-30 08:00 | 2013-11-06 10:00 | 50
106575 | 1560 | ROOF COL. SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-11-06 10:00 | 2013-11-13 12:00 | 50
106576 | 1570 | ISOLATION MATERIAL SUBMITAL | TT_Task | TK_NotStart | 2013-10-16 14:00 | 2013-10-24 08:00 | 50
106577 | 1580 | ISOLATION MATERIAL APPROVAL | TT_Task | TK_NotStart | 2013-10-24 08:00 | 2013-10-31 10:00 | 50
106578 | 1590 | ISOLATION MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2013-10-31 10:00 | 2013-11-07 12:00 | 50
106579 | 1600 | ISOLATION MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2013-11-07 12:00 | 2013-11-23 08:00 | 100
106580 | 1610 | BRICK MATERIAL SUBMITAL | TT_Task | TK_NotStart | 2013-10-31 10:00 | 2013-11-07 12:00 | 50
106581 | 1620 | BRICK MATERIAL APPROVAL | TT_Task | TK_NotStart | 2013-09-21 10:00 | 2013-09-28 12:00 | 50
106582 | 1630 | BRICK MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2013-09-28 12:00 | 2013-10-05 14:00 | 50
106583 | 1640 | BRICK MATERIAL DELIEVERY | TT_Task | TK_NotStart | 2013-10-05 14:00 | 2013-11-18 10:00 | 300
106584 | 1650 | CERMIC MATERIAL SUBMITAL | TT_Task | TK_NotStart | 2013-11-07 12:00 | 2013-11-14 14:00 | 50
106585 | 1660 | CERMIC MATERIAL APPROVAL | TT_Task | TK_NotStart | 2013-10-31 10:00 | 2013-11-07 12:00 | 50
106586 | 1670 | CERMIC MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2013-11-07 12:00 | 2013-11-14 14:00 | 50
106587 | 1680 | CERMIC MATERIAL DELIEVERY | TT_Task | TK_NotStart | 2013-11-14 14:00 | 2014-02-12 14:00 | 600
106588 | 1690 | RED TILES MATERIAL SUBMITAL | TT_Task | TK_NotStart | 2014-10-01 10:00 | 2014-10-08 12:00 | 50
106589 | 1700 | RED TILES MATERIAL APPROVAL | TT_Task | TK_NotStart | 2014-10-08 12:00 | 2014-10-15 14:00 | 50
106590 | 1710 | RED TILES MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2014-10-15 14:00 | 2014-10-23 08:00 | 50
106591 | 1720 | RED TILES MATERIAL DELIEVERY | TT_Task | TK_NotStart | 2014-10-23 08:00 | 2014-11-13 14:00 | 150
106592 | 1730 | MOBILZATION | TT_Task | TK_NotStart | 2013-08-03 08:00 | 2013-09-16 12:00 | 300
106767 | 1740 | B.SLAB SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-08-17 12:00 | 2013-08-24 14:00 | 50
106768 | 1750 | B.SLAB SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-08-24 14:00 | 2013-08-31 16:00 | 50
106769 | 1760 | GR.SLAB SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-09-01 08:00 | 2013-09-09 10:00 | 50
106770 | 1770 | GR.SLAB SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-09-09 10:00 | 2013-09-16 12:00 | 50
106771 | 1780 | 1ST SLAB. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-09-16 12:00 | 2013-09-23 14:00 | 50
106772 | 1790 | 1ST SLAB SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-09-23 14:00 | 2013-09-30 16:00 | 50
106773 | 1800 | 2ND SLAB. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-10-08 10:00 | 2013-10-15 12:00 | 50
106774 | 1810 | 2ND SLAB SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-10-15 12:00 | 2013-10-22 14:00 | 50
106775 | 1820 | 3RD SLAB. SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-10-22 14:00 | 2013-10-29 16:00 | 50
106776 | 1830 | 3RD SLAB SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-10-30 08:00 | 2013-11-06 10:00 | 50
106777 | 1840 | ROOF SLAB SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-11-06 10:00 | 2013-11-13 12:00 | 50
106778 | 1850 | ROOF SLAB SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-11-13 12:00 | 2013-11-20 14:00 | 50
106779 | 1860 | B.MASONARY SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-11-20 14:00 | 2013-11-27 16:00 | 50
106780 | 1870 | B.MASONARY SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-11-30 08:00 | 2013-12-07 10:00 | 50
106781 | 1880 | GR.MASONARY SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-11-30 08:00 | 2013-12-07 10:00 | 50
106782 | 1890 | GR.MASONARY SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-12-07 10:00 | 2013-12-14 12:00 | 50
106783 | 1900 | 1ST.MASONARY SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-12-07 10:00 | 2013-12-14 12:00 | 50
106784 | 1910 | 1ST.MASONARY SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-12-14 12:00 | 2013-12-21 14:00 | 50
106785 | 1920 | 2ND.MASONARY SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-12-21 14:00 | 2013-12-29 16:00 | 50
106786 | 1930 | 2ND.MASONARY SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2013-12-30 08:00 | 2014-01-06 10:00 | 50
106787 | 1940 | 3RD.MASONARY SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2013-12-30 08:00 | 2014-01-06 10:00 | 50
106788 | 1950 | 3RD.MASONARY SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2014-01-06 10:00 | 2014-01-13 12:00 | 50
106789 | 1960 | ROOF MASONARY SHOPDRAWING SUBMITAL | TT_Task | TK_NotStart | 2014-01-06 10:00 | 2014-01-13 12:00 | 50
106790 | 1970 | ROOF MASONARY SHOPDRAWING APPROVAL | TT_Task | TK_NotStart | 2014-01-13 12:00 | 2014-01-20 14:00 | 50
106791 | 1980 | backfill MATERIAL SUBMITAL | TT_Task | TK_NotStart | 2013-10-21 12:00 | 2013-10-28 14:00 | 50
106792 | 1990 | backfill MATERIAL APPROVAL | TT_Task | TK_NotStart | 2013-10-28 14:00 | 2013-11-05 08:00 | 50
106793 | 2000 | backfill MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2013-11-05 08:00 | 2013-11-12 10:00 | 50
106794 | 2010 | backfill MATERIAL PROCURMENT | TT_Task | TK_NotStart | 2013-11-12 10:00 | 2013-11-26 14:00 | 100

## resources
id | name | type | distributionMin | distributionMax | minUnitsPerDay | maxUnitsPerDay | costPerUnitPerHour | costPerUnitPerPeriod | settlementPeriod
10594 | FURNTURE | Labor | 0.02 | 0.02 |  |  | 5000 | 800000 | monthly
10596 | PLUMPER | Labor | 0.028571 | 1.0429 |  | 0.8 | 1500 | 240000 | monthly
10558 | STELL FIXER | Labor | 0.15714 | 70.2857 |  |  | 158.3333 | 25333.3333 | monthly
10564 | MAISON | Labor | 0.33333 | 42.6667 |  |  | 120 | 19200 | monthly
10579 | FALSE CELLING | Labor | 0.5 | 0.9 |  |  | 120 | 19200 | monthly
10557 | CARPENTER | Labor | 0.1 | 70.2857 |  |  | 40 | 6400 | monthly
10582 | TILE MAISON | Labor | 1.2 | 11.5556 |  |  | 35 | 5600 | monthly
10552 | excavator | Equipment | 0.72 | 0.72 |  |  | 30 | 4800 | monthly
10553 | lodr | Equipment | 0.48 | 0.64 |  |  | 20 | 3200 | monthly
10600 | ELECTRICAL | Labor | 0.01 | 2 |  |  | 20 | 3200 | monthly
10554 | truck | Equipment | 0.56 | 0.56 |  |  | 15 | 2400 | monthly
10574 | CERMIC MAISON | Labor | 1.8 | 3.95 |  |  | 15 | 2400 | monthly
10566 | REPLACEMENT | Labor | 21.4286 | 21.4286 |  |  | 13 | 2080 | monthly
10577 | PAINTER | Labor | 1 | 115.05 |  |  | 12 | 1920 | monthly
10573 | PACKING LABOUR | Labor | 0.021429 | 1.0214 |  |  | 10 | 1600 | monthly
10583 | ISOLATION LABOUR | Labor | 13.8 | 13.8 |  |  | 10 | 1600 | monthly
10572 | PLASTER | Labor | 5 | 16.1958 |  |  | 9.2653 | 1482.449 | monthly
10555 | compactor | Equipment | 0.8 | 0.8 |  |  | 5 | 800 | monthly
10588 | FINISHING LABOUR | Labor | 4.6286 | 6.1429 |  |  | 3 | 480 | monthly
-65535 | p6DefaultRes | Labor | 0 | 0 |  |  | 1 | 160 | monthly
10603 | LABOUR | Labor | 0.05 | 2.4616 |  |  | 0.24 | 38.4 | monthly
9977 | TEST PROJECT | Labor | 0 | 0 |  |  | 0 | 0 | monthly
10562 | LABOUR | Labor | 25 | 25 |  |  | 0 | 0 | monthly
10602 | CARPENTER | Labor | 0.02 | 0.6 |  |  | 0 | 0 | monthly
10604 | STEEL FIXER | Labor | 0.06 | 0.63333 |  |  | 0 | 0 | monthly
10605 | MASION | Labor | 0.26667 | 1.18 |  |  | 0 | 0 | monthly
10606 | ISOLATION | Labor | 0.2 | 0.5 |  |  | 0 | 0 | monthly
10607 | PLASTER | Labor | 0.5 | 3.4336 |  |  | 0 | 0 | monthly
10608 | TILE MASION | Labor | 0.24 | 0.63333 |  |  | 0 | 0 | monthly
10609 | FALSE CEILLING | Labor | 0.1 | 0.175 |  |  | 0 | 0 | monthly
10610 | PAINTER | Labor | 0.5 | 2.8956 |  |  | 0 | 0 | monthly
10611 | PLUMPER | Labor | 0.1 | 0.43333 |  |  | 0 | 0 | monthly
10612 | ELECTRCIAN | Labor | 0.1 | 1.2 |  |  | 0 | 0 | monthly
10614 | MARBLE MAISON | Labor | 0.18889 | 1 |  |  | 0 | 0 | monthly
10559 | STEEL | Material | 0.085714 | 8 |  |  | 5000
10560 | CONCRETE | Material | 1.2 | 40 |  |  | 220
10563 | BRICK | Material | 0.036364 | 5.2 |  |  | 250
10565 | ISOLATION | Material | 1600 | 2400 |  |  | 3
10567 | WATER | Material | 0.32 | 80 |  |  | 2
10568 | CEMENT | Material | 0.096 | 1.816 |  |  | 500
10569 | INSOMAT | Material | 27.6 | 200 |  |  | 25
10570 | SAND | Material | 0.08 | 13.7725 |  |  | 12
10571 | WOODEN FRAME | Material | 0.34286 | 9.4857 |  |  | 200
10575 | CERMIC | Material | 3.6 | 31.6 |  |  | 50
10576 | WHITE CEMENT | Material | 0.004 | 0.04 |  |  | 750
10578 | PAINT PACKAGE | Material | 1.99 | 34.8889 |  |  | 50
10580 | STEEL MAKER | Material | 13.3333 | 57.1429 |  |  | 12
10581 | RED TILE | Material | 2.4 | 9.6 |  |  | 90
10584 | THERMAL ISOLATION | Material | 27.6 | 110.4 |  |  | 50
10585 | WINDOWS&DOORS | Material | 0.11429 | 1.4857 |  |  | 150
10586 | WOODEN FLOOR | Material | 0.31429 | 13.6 |  |  | 15
10587 | MARBLE | Material | 5.12 | 36.8 |  |  | 80
10589 | ALMNIUM | Material | 1.2381 | 5.7143 |  |  | 150
10590 | CEMENT TILE | Material | 15.1111 | 60.4444 |  |  | 12
10592 | GRAVITO | Material | 0.2 | 0.75556 |  |  | 1000
10593 | STAIRS | Material | 7.5556 | 15.1111 |  |  | 50
10595 | SAINTARY material | Material | 2 | 16 |  |  | 142.8571
10597 | BOX & PIPE | Material | 0.028571 | 8 |  |  | 83.3333
10598 | ELEC WIRE | Material | 0.04 | 4.8 |  |  | 100
10599 | FINISHING ELEC | Material | 0.02 | 8 |  |  | 0

## taskResources
taskId | taskName | resourceId | resourceName | units | oldUnitsPerHour | ignore(type true) | minUnitsPerHour | maxUnitsPerHour
106071 | EXCAVATION | 10552 | excavator | 72 | 1.0286
106071 | EXCAVATION | 10553 | lodr | 64 | 0.8
106071 | EXCAVATION | 10554 | truck | 56 | 0.8
106222 | REPLACMENT LAYER | 10566 | REPLACEMENT | 1500 | 21.4286
106223 | BACKFILL | 10553 | lodr | 24 | 0.8
106223 | BACKFILL | 10555 | compactor | 40 | 2
106223 | BACKFILL | 10567 | WATER | 500 | 12.5
106224 | P.C | 10557 | CARPENTER | 208 | 3.4667
106224 | P.C | 10560 | CONCRETE | 208 | 20.8
106224 | P.C | 10602 | CARPENTER | 35 | 0.5
106224 | P.C | 10603 | LABOUR | 12 | 0.17143
106225 | R.C | 10557 | CARPENTER | 50 | 5
106225 | R.C | 10558 | STELL FIXER | 96 | 4.8
106225 | R.C | 10559 | STEEL | 30 | 0.25
106225 | R.C | 10560 | CONCRETE | 304 | 30.4
106225 | R.C | 10602 | CARPENTER | 61 | 0.87143
106225 | R.C | 10603 | LABOUR | 46 | 0.575
106225 | R.C | 10604 | STEEL FIXER | 76 | 1.52
106226 | NECK COLUMN | 10557 | CARPENTER | 4920 | 123
106226 | NECK COLUMN | 10558 | STELL FIXER | 4920 | 164
106226 | NECK COLUMN | 10559 | STEEL | 3 | 0.3
106226 | NECK COLUMN | 10560 | CONCRETE | 82 | 8.2
106226 | NECK COLUMN | 10602 | CARPENTER | 42 | 1.05
106226 | NECK COLUMN | 10603 | LABOUR | 9 | 0.3
106226 | NECK COLUMN | 10604 | STEEL FIXER | 28 | 0.93333
106227 | SLAB ON GRADE | 10558 | STELL FIXER | 15 | 1.5
106227 | SLAB ON GRADE | 10559 | STEEL | 1.5 | 0.15
106227 | SLAB ON GRADE | 10560 | CONCRETE | 15 | 1.5
106227 | SLAB ON GRADE | 10602 | CARPENTER | 2 | 0.1
106227 | SLAB ON GRADE | 10603 | LABOUR | 1 | 0.1
106227 | SLAB ON GRADE | 10604 | STEEL FIXER | 3 | 0.3
106228 | DAMP PROOFING | 10569 | INSOMAT | 500 | 25
106228 | DAMP PROOFING | 10606 | ISOLATION | 4 | 0.2
106229 | INSULATION | 10562 | LABOUR | 250 | 25
106229 | INSULATION | 10565 | ISOLATION | 4000 | 400
106229 | INSULATION | 10606 | ISOLATION | 5 | 0.5
106230 | BRICK WORK | 10563 | BRICK | 10 | 1
106230 | BRICK WORK | 10564 | MAISON | 10 | 0.33333
106230 | BRICK WORK | 10567 | WATER | 10 | 0.5
106230 | BRICK WORK | 10568 | CEMENT | 4 | 0.4
106230 | BRICK WORK | 10603 | LABOUR | 4 | 0.13333
106230 | BRICK WORK | 10605 | MASION | 8 | 0.26667
106231 | BASEMENT COLUMN | 10557 | CARPENTER | 32 | 0.64
106231 | BASEMENT COLUMN | 10558 | STELL FIXER | 11 | 0.55
106231 | BASEMENT COLUMN | 10559 | STEEL | 2.84 | 0.284
106231 | BASEMENT COLUMN | 10560 | CONCRETE | 32 | 3.2
106231 | BASEMENT COLUMN | 10602 | CARPENTER | 16 | 0.32
106231 | BASEMENT COLUMN | 10603 | LABOUR | 4 | 0.2
106231 | BASEMENT COLUMN | 10604 | STEEL FIXER | 11 | 0.55
106232 | BASEMENT SLAB | 10557 | CARPENTER | 30 | 1.5
106232 | BASEMENT SLAB | 10558 | STELL FIXER | 160 | 2
106232 | BASEMENT SLAB | 10559 | STEEL | 16 | 1.6
106232 | BASEMENT SLAB | 10560 | CONCRETE | 160 | 16
106232 | BASEMENT SLAB | 10602 | CARPENTER | 6 | 0.3
106232 | BASEMENT SLAB | 10603 | LABOUR | 9 | 0.1125
106232 | BASEMENT SLAB | 10604 | STEEL FIXER | 27 | 0.3375
106233 | GROUND COLUMN | 10557 | CARPENTER | 28 | 0.56
106233 | GROUND COLUMN | 10558 | STELL FIXER | 28 | 0.93333
106233 | GROUND COLUMN | 10559 | STEEL | 3 | 0.3
106233 | GROUND COLUMN | 10560 | CONCRETE | 70 | 1
106233 | GROUND COLUMN | 10602 | CARPENTER | 35 | 0.7
106233 | GROUND COLUMN | 10603 | LABOUR | 8 | 0.26667
106233 | GROUND COLUMN | 10604 | STEEL FIXER | 24 | 0.8
106234 | GROUND SLAB | 10557 | CARPENTER | 38 | 1.9
106234 | GROUND SLAB | 10558 | STELL FIXER | 148 | 2.4667
106234 | GROUND SLAB | 10559 | STEEL | 100 | 10
106234 | GROUND SLAB | 10560 | CONCRETE | 148 | 1.48
106234 | GROUND SLAB | 10602 | CARPENTER | 8 | 0.4
106234 | GROUND SLAB | 10603 | LABOUR | 8 | 0.13333
106234 | GROUND SLAB | 10604 | STEEL FIXER | 25 | 0.41667
106235 | 1ST FLOOR COLUMN | 10557 | CARPENTER | 24 | 0.48
106235 | 1ST FLOOR COLUMN | 10558 | STELL FIXER | 24 | 0.6
106235 | 1ST FLOOR COLUMN | 10559 | STEEL | 3 | 0.3
106235 | 1ST FLOOR COLUMN | 10560 | CONCRETE | 50 | 5
106235 | 1ST FLOOR COLUMN | 10602 | CARPENTER | 25 | 0.5
106235 | 1ST FLOOR COLUMN | 10603 | LABOUR | 6 | 0.15
106235 | 1ST FLOOR COLUMN | 10604 | STEEL FIXER | 17 | 0.425
106236 | 1ST FLOOR SLAB | 10557 | CARPENTER | 45 | 2.25
106236 | 1ST FLOOR SLAB | 10558 | STELL FIXER | 155 | 3.875
106236 | 1ST FLOOR SLAB | 10559 | STEEL | 100 | 10
106236 | 1ST FLOOR SLAB | 10560 | CONCRETE | 155 | 15.5
106236 | 1ST FLOOR SLAB | 10602 | CARPENTER | 9 | 0.45
106236 | 1ST FLOOR SLAB | 10603 | LABOUR | 9 | 0.225
106236 | 1ST FLOOR SLAB | 10604 | STEEL FIXER | 26 | 0.65
106237 | 2ND FLOOR COLUMN | 10557 | CARPENTER | 22 | 0.44
106237 | 2ND FLOOR COLUMN | 10558 | STELL FIXER | 22 | 0.55
106237 | 2ND FLOOR COLUMN | 10559 | STEEL | 2.5 | 0.035714
106237 | 2ND FLOOR COLUMN | 10560 | CONCRETE | 22 | 2.2
106237 | 2ND FLOOR COLUMN | 10602 | CARPENTER | 11 | 0.22
106237 | 2ND FLOOR COLUMN | 10603 | LABOUR | 3 | 0.075
106237 | 2ND FLOOR COLUMN | 10604 | STEEL FIXER | 8 | 0.2
106238 | 2ND FLOOR SLAB | 10557 | CARPENTER | 125 | 2.5
106238 | 2ND FLOOR SLAB | 10558 | STELL FIXER | 176 | 3.52
106238 | 2ND FLOOR SLAB | 10559 | STEEL | 20 | 2
106238 | 2ND FLOOR SLAB | 10560 | CONCRETE | 176 | 17.6
106238 | 2ND FLOOR SLAB | 10602 | CARPENTER | 36 | 0.72
106238 | 2ND FLOOR SLAB | 10603 | LABOUR | 10 | 0.2
106238 | 2ND FLOOR SLAB | 10604 | STEEL FIXER | 30 | 0.6
106239 | 3RD FLOOR COLUMN | 10557 | CARPENTER | 20 | 0.5
106239 | 3RD FLOOR COLUMN | 10558 | STELL FIXER | 20 | 0.5
106239 | 3RD FLOOR COLUMN | 10559 | STEEL | 2.5 | 0.25
106239 | 3RD FLOOR COLUMN | 10560 | CONCRETE | 20 | 2
106239 | 3RD FLOOR COLUMN | 10602 | CARPENTER | 10 | 0.25
106239 | 3RD FLOOR COLUMN | 10603 | LABOUR | 2 | 0.05
106239 | 3RD FLOOR COLUMN | 10604 | STEEL FIXER | 7 | 0.175
106240 | 3RD FLOOR SLAB | 10557 | CARPENTER | 40 | 2
106240 | 3RD FLOOR SLAB | 10558 | STELL FIXER | 130 | 2.1667
106240 | 3RD FLOOR SLAB | 10559 | STEEL | 13 | 1.3
106240 | 3RD FLOOR SLAB | 10560 | CONCRETE | 40 | 4
106240 | 3RD FLOOR SLAB | 10602 | CARPENTER | 8 | 0.4
106240 | 3RD FLOOR SLAB | 10603 | LABOUR | 9 | 0.15
106240 | 3RD FLOOR SLAB | 10604 | STEEL FIXER | 26 | 0.43333
106241 | ROOF FLOOR COLUMN | 10557 | CARPENTER | 5 | 0.25
106241 | ROOF FLOOR COLUMN | 10558 | STELL FIXER | 15 | 0.5
106241 | ROOF FLOOR COLUMN | 10559 | STEEL | 2 | 0.2
106241 | ROOF FLOOR COLUMN | 10560 | CONCRETE | 15 | 1.5
106241 | ROOF FLOOR COLUMN | 10602 | CARPENTER | 1 | 0.05
106241 | ROOF FLOOR COLUMN | 10603 | LABOUR | 1 | 0.033333
106241 | ROOF FLOOR COLUMN | 10604 | STEEL FIXER | 3 | 0.1
106242 | ROOF FLOOR SLAB | 10557 | CARPENTER | 5 | 0.25
106242 | ROOF FLOOR SLAB | 10558 | STELL FIXER | 15 | 0.5
106242 | ROOF FLOOR SLAB | 10559 | STEEL | 2 | 0.2
106242 | ROOF FLOOR SLAB | 10560 | CONCRETE | 15 | 1.5
106242 | ROOF FLOOR SLAB | 10602 | CARPENTER | 1 | 0.05
106242 | ROOF FLOOR SLAB | 10603 | LABOUR | 1 | 0.033333
106242 | ROOF FLOOR SLAB | 10604 | STEEL FIXER | 3 | 0.1
106243 | B. FLOOR MASONARY WORK | 10563 | BRICK | 8.8 | 0.88
106243 | B. FLOOR MASONARY WORK | 10564 | MAISON | 1280 | 42.6667
106243 | B. FLOOR MASONARY WORK | 10567 | WATER | 6 | 0.6
106243 | B. FLOOR MASONARY WORK | 10568 | CEMENT | 2 | 0.2
106243 | B. FLOOR MASONARY WORK | 10570 | SAND | 6 | 0.6
106243 | B. FLOOR MASONARY WORK | 10603 | LABOUR | 10 | 0.33333
106243 | B. FLOOR MASONARY WORK | 10605 | MASION | 16 | 0.53333
106244 | WINDOWS&DOORS | 10571 | WOODEN FRAME | 26 | 0.18571
106245 | PLASTER | 10567 | WATER | 20 | 2
106245 | PLASTER | 10568 | CEMENT | 3 | 0.3
106245 | PLASTER | 10570 | SAND | 10 | 1
106245 | PLASTER | 10572 | PLASTER | 980 | 7
106245 | PLASTER | 10573 | PACKING LABOUR | 3 | 0.15
106245 | PLASTER | 10603 | LABOUR | 28 | 0.2
106245 | PLASTER | 10607 | PLASTER | 82 | 0.58571
106246 | CERMIC | 10567 | WATER | 2 | 0.2
106246 | CERMIC | 10568 | CEMENT | 1 | 0.1
106246 | CERMIC | 10570 | SAND | 3 | 0.3
106246 | CERMIC | 10573 | PACKING LABOUR | 50 | 5
106246 | CERMIC | 10574 | CERMIC MAISON | 90 | 1.8
106246 | CERMIC | 10575 | CERMIC | 90 | 9
106246 | CERMIC | 10576 | WHITE CEMENT | 0.1 | 0.01
106246 | CERMIC | 10603 | LABOUR | 6 | 0.12
106246 | CERMIC | 10608 | TILE MASION | 12 | 0.24
106247 | INTIAL PAINTING | 10577 | PAINTER | 600 | 5
106247 | INTIAL PAINTING | 10578 | PAINT PACKAGE | 120 | 4
106247 | INTIAL PAINTING | 10603 | LABOUR | 15 | 0.125
106247 | INTIAL PAINTING | 10610 | PAINTER | 60 | 0.5
106248 | GR. FLOOR MASONARY WORK | 10563 | BRICK | 50.6 | 5.06
106248 | GR. FLOOR MASONARY WORK | 10564 | MAISON | 920 | 10.2222
106248 | GR. FLOOR MASONARY WORK | 10567 | WATER | 37 | 3.7
106248 | GR. FLOOR MASONARY WORK | 10568 | CEMENT | 12 | 1.2
106248 | GR. FLOOR MASONARY WORK | 10570 | SAND | 37 | 3.7
106248 | GR. FLOOR MASONARY WORK | 10603 | LABOUR | 67 | 0.74444
106248 | GR. FLOOR MASONARY WORK | 10605 | MASION | 100 | 1.1111
106249 | WINDOWS&DOORS | 10571 | WOODEN FRAME | 14 | 0.1
106250 | PLASTER | 10567 | WATER | 34 | 0.17
106250 | PLASTER | 10568 | CEMENT | 5.5 | 0.55
106250 | PLASTER | 10570 | SAND | 20 | 2
106250 | PLASTER | 10572 | PLASTER | 1698 | 8.49
106250 | PLASTER | 10603 | LABOUR | 200 | 1
106250 | PLASTER | 10607 | PLASTER | 200 | 1
106251 | MATEL LATH | 10579 | FALSE CELLING | 34 | 0.85
106252 | CERMIC | 10567 | WATER | 11 | 0.11
106252 | CERMIC | 10568 | CEMENT | 2.8 | 0.28
106252 | CERMIC | 10570 | SAND | 10 | 1
106252 | CERMIC | 10574 | CERMIC MAISON | 270 | 2.7
106252 | CERMIC | 10575 | CERMIC | 270 | 27
106252 | CERMIC | 10576 | WHITE CEMENT | 0.5 | 0.005
106252 | CERMIC | 10603 | LABOUR | 17 | 0.17
106252 | CERMIC | 10608 | TILE MASION | 34 | 0.34
106253 | INTIAL PAINTING | 10577 | PAINTER | 994 | 4.97
106253 | INTIAL PAINTING | 10578 | PAINT PACKAGE | 199 | 0.995
106253 | INTIAL PAINTING | 10603 | LABOUR | 25 | 0.125
106253 | INTIAL PAINTING | 10610 | PAINTER | 100 | 0.5
106254 | 1ST FLOOR MASONARY WORK | 10563 | BRICK | 65 | 6.5
106254 | 1ST FLOOR MASONARY WORK | 10564 | MAISON | 1012 | 9.2
106254 | 1ST FLOOR MASONARY WORK | 10567 | WATER | 41 | 4.1
106254 | 1ST FLOOR MASONARY WORK | 10568 | CEMENT | 13 | 1.3
106254 | 1ST FLOOR MASONARY WORK | 10570 | SAND | 41 | 4.1
106254 | 1ST FLOOR MASONARY WORK | 10605 | MASION | 67 | 0.60909
106255 | WINDOWS&DOORS | 10571 | WOODEN FRAME | 14 | 0.1
106256 | PLASTER | 10567 | WATER | 55 | 5.5
106256 | PLASTER | 10568 | CEMENT | 8 | 0.8
106256 | PLASTER | 10570 | SAND | 27 | 2.7
106256 | PLASTER | 10572 | PLASTER | 2664 | 10.656
106256 | PLASTER | 10603 | LABOUR | 74 | 0.296
106256 | PLASTER | 10607 | PLASTER | 222 | 0.888
106257 | MATEL LATH | 10579 | FALSE CELLING | 34 | 0.85
106257 | MATEL LATH | 10603 | LABOUR | 2 | 0.05
106257 | MATEL LATH | 10609 | FALSE CEILLING | 6 | 0.15
106258 | CERMIC | 10567 | WATER | 12 | 1.2
106258 | CERMIC | 10568 | CEMENT | 3 | 0.03
106258 | CERMIC | 10570 | SAND | 9 | 0.9
106258 | CERMIC | 10574 | CERMIC MAISON | 290 | 2.9
106258 | CERMIC | 10575 | CERMIC | 290 | 29
106258 | CERMIC | 10576 | WHITE CEMENT | 0.3 | 0.03
106258 | CERMIC | 10603 | LABOUR | 16 | 0.16
106258 | CERMIC | 10608 | TILE MASION | 32 | 0.32
106259 | INTIAL PAINTING | 10577 | PAINTER | 1440 | 9.6
106259 | INTIAL PAINTING | 10578 | PAINT PACKAGE | 288 | 1.92
106259 | INTIAL PAINTING | 10603 | LABOUR | 36 | 0.24
106259 | INTIAL PAINTING | 10610 | PAINTER | 144 | 0.96
106260 | 2ND FLOOR MASONARY WORK | 10563 | BRICK | 58 | 0.58
106260 | 2ND FLOOR MASONARY WORK | 10564 | MAISON | 1040 | 10.4
106260 | 2ND FLOOR MASONARY WORK | 10567 | WATER | 42 | 0.42
106260 | 2ND FLOOR MASONARY WORK | 10568 | CEMENT | 13.5 | 0.135
106260 | 2ND FLOOR MASONARY WORK | 10570 | SAND | 42 | 0.42
106260 | 2ND FLOOR MASONARY WORK | 10603 | LABOUR | 70 | 0.7
106260 | 2ND FLOOR MASONARY WORK | 10605 | MASION | 104 | 1.04
106261 | WINDOWS&DOORS | 10571 | WOODEN FRAME | 14 | 0.1
106262 | PLASTER | 10567 | WATER | 56 | 5.6
106262 | PLASTER | 10568 | CEMENT | 8.5 | 0.85
106262 | PLASTER | 10570 | SAND | 28 | 2.8
106262 | PLASTER | 10572 | PLASTER | 2768 | 10.6462
106262 | PLASTER | 10603 | LABOUR | 77 | 0.29615
106262 | PLASTER | 10607 | PLASTER | 231 | 0.88846
106263 | MATEL LATH | 10579 | FALSE CELLING | 36 | 0.9
106263 | MATEL LATH | 10603 | LABOUR | 3 | 0.075
106263 | MATEL LATH | 10609 | FALSE CEILLING | 7 | 0.175
106264 | CERMIC | 10567 | WATER | 16 | 1.6
106264 | CERMIC | 10568 | CEMENT | 4 | 0.4
106264 | CERMIC | 10570 | SAND | 12 | 1.2
106264 | CERMIC | 10574 | CERMIC MAISON | 395 | 3.95
106264 | CERMIC | 10575 | CERMIC | 395 | 39.5
106264 | CERMIC | 10576 | WHITE CEMENT | 0.1 | 0.01
106264 | CERMIC | 10603 | LABOUR | 25 | 0.25
106264 | CERMIC | 10608 | TILE MASION | 50 | 0.5
106265 | INTIAL PAINTING | 10577 | PAINTER | 18408 | 115.05
106265 | INTIAL PAINTING | 10578 | PAINT PACKAGE | 307 | 1.9187
106265 | INTIAL PAINTING | 10603 | LABOUR | 39 | 0.24375
106265 | INTIAL PAINTING | 10610 | PAINTER | 154 | 0.9625
106266 | 3RD FLOOR MASONARY WORK | 10563 | BRICK | 65 | 6.5
106266 | 3RD FLOOR MASONARY WORK | 10564 | MAISON | 1180 | 11.8
106266 | 3RD FLOOR MASONARY WORK | 10567 | WATER | 48 | 4.8
106266 | 3RD FLOOR MASONARY WORK | 10568 | CEMENT | 15.5 | 1.55
106266 | 3RD FLOOR MASONARY WORK | 10570 | SAND | 48 | 4.8
106266 | 3RD FLOOR MASONARY WORK | 10603 | LABOUR | 79 | 0.79
106266 | 3RD FLOOR MASONARY WORK | 10605 | MASION | 118 | 1.18
106267 | WINDOWS&DOORS | 10571 | WOODEN FRAME | 166 | 1.1857
106268 | PLASTER | 10567 | WATER | 48 | 4.8
106268 | PLASTER | 10568 | CEMENT | 7.5 | 0.75
106268 | PLASTER | 10570 | SAND | 24 | 2.4
106268 | PLASTER | 10572 | PLASTER | 2380 | 10.3478
106268 | PLASTER | 10603 | LABOUR | 67 | 0.2913
106268 | PLASTER | 10605 | MASION | 199 | 0.86522
106269 | MATEL LATH | 10579 | FALSE CELLING | 30 | 0.75
106269 | MATEL LATH | 10603 | LABOUR | 3 | 0.075
106269 | MATEL LATH | 10609 | FALSE CEILLING | 6 | 0.15
106270 | CERMIC | 10567 | WATER | 15 | 1.5
106270 | CERMIC | 10568 | CEMENT | 3.6 | 0.36
106270 | CERMIC | 10570 | SAND | 11 | 1.1
106270 | CERMIC | 10574 | CERMIC MAISON | 360 | 3.2727
106270 | CERMIC | 10576 | WHITE CEMENT | 0.36 | 0.036
106270 | CERMIC | 10603 | LABOUR | 23 | 0.20909
106270 | CERMIC | 10608 | TILE MASION | 45 | 0.40909
106271 | INTIAL PAINTING | 10577 | PAINTER | 90 | 1
106271 | INTIAL PAINTING | 10578 | PAINT PACKAGE | 262 | 2.9111
106271 | INTIAL PAINTING | 10603 | LABOUR | 33 | 0.36667
106271 | INTIAL PAINTING | 10610 | PAINTER | 131 | 1.4556
106272 | ROOF FLOOR MASONARY WORK | 10563 | BRICK | 8.8 | 0.88
106272 | ROOF FLOOR MASONARY WORK | 10564 | MAISON | 160 | 16
106272 | ROOF FLOOR MASONARY WORK | 10567 | WATER | 7 | 0.7
106272 | ROOF FLOOR MASONARY WORK | 10568 | CEMENT | 2.08 | 0.104
106272 | ROOF FLOOR MASONARY WORK | 10570 | SAND | 7 | 0.7
106272 | ROOF FLOOR MASONARY WORK | 10603 | LABOUR | 11 | 0.55
106272 | ROOF FLOOR MASONARY WORK | 10605 | MASION | 16 | 0.8
106273 | WINDOWS&DOORS | 10571 | WOODEN FRAME | 4 | 0.057143
106274 | PLASTER | 10567 | WATER | 20 | 2
106274 | PLASTER | 10568 | CEMENT | 2.2 | 0.22
106274 | PLASTER | 10570 | SAND | 10 | 1
106274 | PLASTER | 10572 | PLASTER | 720 | 9
106274 | PLASTER | 10603 | LABOUR | 80 | 1
106274 | PLASTER | 10607 | PLASTER | 80 | 1
106275 | MATEL LATH | 10579 | FALSE CELLING | 20 | 0.5
106275 | MATEL LATH | 10603 | LABOUR | 1 | 0.025
106275 | MATEL LATH | 10609 | FALSE CEILLING | 4 | 0.1
106276 | PROOFING | 10569 | INSOMAT | 552 | 55.2
106276 | PROOFING | 10583 | ISOLATION LABOUR | 552 | 13.8
106276 | PROOFING | 10603 | LABOUR | 4 | 0.1
106276 | PROOFING | 10606 | ISOLATION | 11 | 0.275
106277 | THERMAL INSULATION | 10584 | THERMAL ISOLATION | 552 | 13.8
106277 | THERMAL INSULATION | 10603 | LABOUR | 4 | 0.1
106277 | THERMAL INSULATION | 10606 | ISOLATION | 11 | 0.275
106278 | P. C. SCREED | 10560 | CONCRETE | 50 | 5
106278 | P. C. SCREED | 10603 | LABOUR | 2 | 0.2
106279 | PLASTER | 10567 | WATER | 30 | 3
106279 | PLASTER | 10568 | CEMENT | 3.85 | 0.385
106279 | PLASTER | 10570 | SAND | 15 | 1.5
106279 | PLASTER | 10572 | PLASTER | 1280 | 7.5294
106279 | PLASTER | 10603 | LABOUR | 94 | 0.55294
106279 | PLASTER | 10607 | PLASTER | 142 | 0.83529
106280 | CERETAL WORK | 10580 | STEEL MAKER | 1000 | 7.1429
106281 | PLASTER | 10567 | WATER | 80 | 8
106281 | PLASTER | 10568 | CEMENT | 12 | 1.2
106281 | PLASTER | 10570 | SAND | 40 | 4
106281 | PLASTER | 10572 | PLASTER | 4000 | 7.2727
106281 | PLASTER | 10603 | LABOUR | 667 | 1.2127
106281 | PLASTER | 10607 | PLASTER | 1000 | 1.8182
106282 | RED TILES | 10567 | WATER | 2 | 0.2
106282 | RED TILES | 10568 | CEMENT | 0.6 | 0.06
106282 | RED TILES | 10570 | SAND | 0.5 | 0.05
106282 | RED TILES | 10581 | RED TILE | 60 | 6
106282 | RED TILES | 10582 | TILE MAISON | 60 | 1.2
106282 | RED TILES | 10603 | LABOUR | 6 | 0.12
106282 | RED TILES | 10608 | TILE MASION | 12 | 0.24
106283 | WINDOWS&DOORS | 10585 | WINDOWS&DOORS | 26 | 0.18571
106284 | PAINTING | 10577 | PAINTER | 600 | 6
106284 | PAINTING | 10578 | PAINT PACKAGE | 60 | 6
106284 | PAINTING | 10603 | LABOUR | 15 | 0.15
106284 | PAINTING | 10607 | PLASTER | 60 | 0.6
106285 | WOODEN FLOORS | 10586 | WOODEN FLOOR | 68 | 0.97143
106286 | MARBLE FLOORS | 10567 | WATER | 13 | 1.3
106286 | MARBLE FLOORS | 10568 | CEMENT | 2 | 0.2
106286 | MARBLE FLOORS | 10570 | SAND | 26 | 2.6
106286 | MARBLE FLOORS | 10582 | TILE MAISON | 256 | 2.56
106286 | MARBLE FLOORS | 10587 | MARBLE | 256 | 25.6
106286 | MARBLE FLOORS | 10603 | LABOUR | 16 | 0.16
106286 | MARBLE FLOORS | 10614 | MARBLE MAISON | 32 | 0.32
106287 | FINISHING FLOORS | 10588 | FINISHING LABOUR | 324 | 4.6286
106287 | FINISHING FLOORS | 10603 | LABOUR | 14 | 0.2
106288 | ALUMINUM | 10589 | ALMNIUM | 74 | 0.35238
106289 | DOOR | 10585 | WINDOWS&DOORS | 21 | 0.1
106290 | PAINTING | 10577 | PAINTER | 992 | 9.0182
106290 | PAINTING | 10578 | PAINT PACKAGE | 100 | 0.90909
106290 | PAINTING | 10603 | LABOUR | 25 | 0.22727
106290 | PAINTING | 10610 | PAINTER | 100 | 0.90909
106291 | WOODEN FLOORS | 10586 | WOODEN FLOOR | 216 | 1.5429
106292 | MARBLE FLOORS | 10567 | WATER | 11 | 1.1
106292 | MARBLE FLOORS | 10568 | CEMENT | 2.5 | 0.25
106292 | MARBLE FLOORS | 10570 | SAND | 22 | 2.2
106292 | MARBLE FLOORS | 10582 | TILE MAISON | 214 | 3.0571
106292 | MARBLE FLOORS | 10587 | MARBLE | 214 | 21.4
106292 | MARBLE FLOORS | 10603 | LABOUR | 13 | 0.18571
106292 | MARBLE FLOORS | 10614 | MARBLE MAISON | 27 | 0.38571
106293 | FINISHING FLOORS | 10588 | FINISHING LABOUR | 430 | 6.1429
106293 | FINISHING FLOORS | 10603 | LABOUR | 14 | 0.2
106294 | ALUMINUM | 10589 | ALMNIUM | 130 | 0.61905
106295 | DOOR | 10585 | WINDOWS&DOORS | 29 | 0.1381
106296 | PAINTING | 10577 | PAINTER | 1440 | 14.4
106296 | PAINTING | 10578 | PAINT PACKAGE | 145 | 1.45
106296 | PAINTING | 10603 | LABOUR | 29 | 0.29
106296 | PAINTING | 10610 | PAINTER | 144 | 1.44
106297 | WOODEN FLOORS | 10586 | WOODEN FLOOR | 216 | 1.5429
106298 | MARBLE FLOORS | 10567 | WATER | 10 | 1
106298 | MARBLE FLOORS | 10568 | CEMENT | 2 | 0.2
106298 | MARBLE FLOORS | 10570 | SAND | 40 | 4
106298 | MARBLE FLOORS | 10582 | TILE MAISON | 200 | 20
106298 | MARBLE FLOORS | 10587 | MARBLE | 200 | 4
106298 | MARBLE FLOORS | 10603 | LABOUR | 13 | 0.26
106298 | MARBLE FLOORS | 10614 | MARBLE MAISON | 50 | 1
106299 | FINISHING FLOORS | 10588 | FINISHING LABOUR | 416 | 5.9429
106299 | FINISHING FLOORS | 10603 | LABOUR | 14 | 0.2
106300 | ALUMINUM | 10589 | ALMNIUM | 150 | 0.71429
106301 | DOOR | 10586 | WOODEN FLOOR | 33 | 0.15714
106302 | PAINTING | 10577 | PAINTER | 110 | 1
106302 | PAINTING | 10578 | PAINT PACKAGE | 110 | 11
106302 | PAINTING | 10603 | LABOUR | 28 | 0.25455
106302 | PAINTING | 10610 | PAINTER | 110 | 1
106303 | WOODEN FLOORS | 10586 | WOODEN FLOOR | 160 | 1.1429
106304 | MARBLE FLOORS | 10567 | WATER | 23 | 2.3
106304 | MARBLE FLOORS | 10568 | CEMENT | 2.5 | 0.25
106304 | MARBLE FLOORS | 10570 | SAND | 46 | 4.6
106304 | MARBLE FLOORS | 10582 | TILE MAISON | 230 | 4.6
106304 | MARBLE FLOORS | 10587 | MARBLE | 230 | 23
106304 | MARBLE FLOORS | 10603 | LABOUR | 8 | 0.16
106304 | MARBLE FLOORS | 10614 | MARBLE MAISON | 29 | 0.58
106305 | FINISHING FLOORS | 10588 | FINISHING LABOUR | 380 | 5.4286
106305 | FINISHING FLOORS | 10603 | LABOUR | 14 | 0.2
106306 | ALUMINUM | 10589 | ALMNIUM | 144 | 0.68571
106307 | DOOR | 10585 | WINDOWS&DOORS | 23 | 0.10952
106308 | PAINTING | 10577 | PAINTER | 1310 | 14.5556
106308 | PAINTING | 10578 | PAINT PACKAGE | 132 | 13.2
106308 | PAINTING | 10603 | LABOUR | 33 | 0.36667
106308 | PAINTING | 10610 | PAINTER | 131 | 1.4556
106309 | CEMENT TILES | 10567 | WATER | 30 | 3
106309 | CEMENT TILES | 10568 | CEMENT | 7 | 0.7
106309 | CEMENT TILES | 10570 | SAND | 75 | 7.5
106309 | CEMENT TILES | 10582 | TILE MAISON | 680 | 7.5556
106309 | CEMENT TILES | 10590 | CEMENT TILE | 680 | 68
106309 | CEMENT TILES | 10603 | LABOUR | 29 | 0.32222
106309 | CEMENT TILES | 10608 | TILE MASION | 57 | 0.63333
106310 | FACADES PLASTER | 10567 | WATER | 40 | 4
106310 | FACADES PLASTER | 10572 | PLASTER | 360 | 4
106310 | FACADES PLASTER | 10592 | GRAVITO | 4 | 0.4
106310 | FACADES PLASTER | 10603 | LABOUR | 23 | 0.25556
106310 | FACADES PLASTER | 10607 | PLASTER | 90 | 1
106311 | DOOR | 10585 | WINDOWS&DOORS | 4 | 0.057143
106312 | CERETAL WORK | 10580 | STEEL MAKER | 1400 | 6.6667
106313 | PLASTER COLORD | 10567 | WATER | 50 | 5
106313 | PLASTER COLORD | 10572 | PLASTER | 640 | 4.9231
106313 | PLASTER COLORD | 10592 | GRAVITO | 6.5 | 0.65
106313 | PLASTER COLORD | 10603 | LABOUR | 40 | 0.30769
106313 | PLASTER COLORD | 10607 | PLASTER | 80 | 0.61538
106314 | MARBLE FLOORS | 10567 | WATER | 20 | 2
106314 | MARBLE FLOORS | 10568 | CEMENT | 1.5 | 0.15
106314 | MARBLE FLOORS | 10570 | SAND | 15 | 1.5
106314 | MARBLE FLOORS | 10582 | TILE MAISON | 150 | 1.875
106314 | MARBLE FLOORS | 10587 | MARBLE | 150 | 15
106314 | MARBLE FLOORS | 10603 | LABOUR | 15 | 0.1875
106314 | MARBLE FLOORS | 10614 | MARBLE MAISON | 30 | 0.375
106315 | MARBLE STAIRS | 10593 | STAIRS | 170 | 1.8889
106315 | MARBLE STAIRS | 10603 | LABOUR | 8 | 0.088889
106315 | MARBLE STAIRS | 10614 | MARBLE MAISON | 17 | 0.18889
106316 | FACADES PLASTER DAHARA | 10567 | WATER | 100 | 0.25
106316 | FACADES PLASTER DAHARA | 10572 | PLASTER | 2000 | 5
106316 | FACADES PLASTER DAHARA | 10592 | GRAVITO | 20 | 0.05
106316 | FACADES PLASTER DAHARA | 10603 | LABOUR | 100 | 0.25
106316 | FACADES PLASTER DAHARA | 10607 | PLASTER | 200 | 0.5
106317 | BARGOLAS | 10594 | FURNTURE | 1 | 0.02
106318 | INTIAL SAINTARY WORK | 10595 | SAINTARY material | 70 | 7
106318 | INTIAL SAINTARY WORK | 10596 | PLUMPER | 2 | 0.028571
106318 | INTIAL SAINTARY WORK | 10603 | LABOUR | 7 | 0.1
106318 | INTIAL SAINTARY WORK | 10611 | PLUMPER | 14 | 0.2
106319 | FINAL SAINTARY WORK | 10595 | SAINTARY material | 30 | 3
106319 | FINAL SAINTARY WORK | 10596 | PLUMPER | 30 | 1
106319 | FINAL SAINTARY WORK | 10611 | PLUMPER | 7 | 0.23333
106320 | INTIAL SAINTARY WORK | 10595 | SAINTARY material | 70 | 7
106320 | INTIAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.042857
106320 | INTIAL SAINTARY WORK | 10603 | LABOUR | 7 | 0.1
106320 | INTIAL SAINTARY WORK | 10611 | PLUMPER | 14 | 0.2
106321 | FINAL SAINTARY WORK | 10595 | SAINTARY material | 30 | 3
106321 | FINAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.1
106321 | FINAL SAINTARY WORK | 10611 | PLUMPER | 7 | 0.23333
106322 | INTIAL SAINTARY WORK | 10595 | SAINTARY material | 70 | 7
106322 | INTIAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.042857
106322 | INTIAL SAINTARY WORK | 10603 | LABOUR | 7 | 0.1
106322 | INTIAL SAINTARY WORK | 10611 | PLUMPER | 14 | 0.2
106323 | FINAL SAINTARY WORK | 10595 | SAINTARY material | 30 | 3
106323 | FINAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.1
106323 | FINAL SAINTARY WORK | 10611 | PLUMPER | 7 | 0.23333
106324 | INTIAL SAINTARY WORK | 10595 | SAINTARY material | 70 | 7
106324 | INTIAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.042857
106324 | INTIAL SAINTARY WORK | 10603 | LABOUR | 7 | 0.1
106324 | INTIAL SAINTARY WORK | 10611 | PLUMPER | 14 | 0.2
106325 | FINAL SAINTARY WORK | 10595 | SAINTARY material | 30 | 3
106325 | FINAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.1
106325 | FINAL SAINTARY WORK | 10611 | PLUMPER | 7 | 0.23333
106326 | INTIAL SAINTARY WORK | 10595 | SAINTARY material | 70 | 7
106326 | INTIAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.042857
106326 | INTIAL SAINTARY WORK | 10603 | LABOUR | 7 | 0.1
106326 | INTIAL SAINTARY WORK | 10611 | PLUMPER | 14 | 0.2
106327 | FINAL SAINTARY WORK | 10595 | SAINTARY material | 30 | 3
106327 | FINAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.1
106327 | FINAL SAINTARY WORK | 10611 | PLUMPER | 7 | 0.23333
106328 | INTIAL SAINTARY WORK | 10595 | SAINTARY material | 30 | 3
106328 | INTIAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.1
106328 | INTIAL SAINTARY WORK | 10603 | LABOUR | 1 | 0.033333
106328 | INTIAL SAINTARY WORK | 10611 | PLUMPER | 3 | 0.1
106329 | FINAL SAINTARY WORK | 10595 | SAINTARY material | 20 | 2
106329 | FINAL SAINTARY WORK | 10596 | PLUMPER | 3 | 0.15
106329 | FINAL SAINTARY WORK | 10611 | PLUMPER | 2 | 0.1
106330 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 30 | 3
106330 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 100 | 1
106330 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 100 | 1
106330 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 100 | 1
106331 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 30 | 3
106331 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 50 | 1
106331 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106331 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106332 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 70 | 2.3333
106332 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 7 | 0.1
106332 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 3.5 | 0.05
106332 | FINAL ELECTRICAL FIX | 10611 | PLUMPER | 14 | 0.2
106333 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 100 | 10
106333 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 50 | 0.5
106333 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106333 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 20 | 0.2
106334 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106334 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 50 | 1
106334 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106334 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106335 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.1
106335 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 50 | 0.5
106335 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106335 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 100 | 1
106336 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 1 | 0.1
106336 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 55 | 0.55
106336 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106336 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 20 | 0.2
106337 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106337 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 55 | 1.1
106337 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106337 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106338 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.1
106338 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 55 | 0.55
106338 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106338 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.1
106339 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 1 | 0.1
106339 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 60 | 0.6
106339 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106339 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 20 | 0.2
106340 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106340 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 60 | 1.2
106340 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106340 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106341 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.1
106341 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 60 | 0.6
106341 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106341 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.1
106342 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 1 | 0.1
106342 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 60 | 0.6
106342 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106342 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 20 | 0.2
106343 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106343 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 60 | 1.2
106343 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106343 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106344 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.01
106344 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 60 | 0.6
106344 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106344 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.1
106345 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 1 | 0.1
106345 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 20 | 0.2
106345 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106345 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 20 | 0.2
106346 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106346 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 20 | 0.4
106346 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106346 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106347 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.1
106347 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 20 | 0.28571
106347 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 7 | 0.1
106347 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 7 | 0.1
106348 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 1 | 0.1
106348 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 1 | 0.01
106348 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106348 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 20 | 0.2
106349 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106349 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 1 | 0.02
106349 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106349 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106350 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.1
106350 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 1 | 0.01
106350 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 10 | 0.1
106350 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.1
106351 | 1ST ELECTRICAL FIX | 10597 | BOX & PIPE | 1 | 0.1
106351 | 1ST ELECTRICAL FIX | 10600 | ELECTRICAL | 4 | 0.057143
106351 | 1ST ELECTRICAL FIX | 10603 | LABOUR | 7 | 0.1
106351 | 1ST ELECTRICAL FIX | 10612 | ELECTRCIAN | 14 | 0.2
106352 | 2ND ELECTRICAL FIX | 10598 | ELEC WIRE | 1 | 0.1
106352 | 2ND ELECTRICAL FIX | 10600 | ELECTRICAL | 4 | 0.08
106352 | 2ND ELECTRICAL FIX | 10603 | LABOUR | 5 | 0.1
106352 | 2ND ELECTRICAL FIX | 10612 | ELECTRCIAN | 10 | 0.2
106353 | FINAL ELECTRICAL FIX | 10599 | FINISHING ELEC | 1 | 0.1
106353 | FINAL ELECTRICAL FIX | 10600 | ELECTRICAL | 4 | 0.1
106353 | FINAL ELECTRICAL FIX | 10603 | LABOUR | 4 | 0.1
106353 | FINAL ELECTRICAL FIX | 10612 | ELECTRCIAN | 4 | 0.1

## calendars
id | name | mustStartBefore
6690 | test project | 0

## project
name | dataDate | planStart | planFinish | planDurationDays | baselineStart | baselineFinish | baselineDurationDays
TP | 2013-08-03 00:00 | 2013-08-03 08:00 | 2015-02-19 12:00 | 565.5 | 2013-08-03 08:00 | 2015-02-19 12:00 | 565.5